## RAID LOG
| RAID Log | [9 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 2 | 0 | 0 | 0 | 0 | 0
| Project title: | Predictive Anlaysis |  | Project Id: |  | Project Manager: | Jayanth G S |  |  | Assumption | 2 | 0 | 0 | 0 | 0 | 0
[10 empty] | Issue | 1 | 0 | 0 | 0 | 0 | 0
|  |  |  | Last Updated date: | 2020-07-27 | Project Team Lead: |  |  |  | Dependency | 1 | 0 | 0 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 6 |  |  |  |  | 0
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Assumption | probabilistic assumptions to ground statistical inference about the model parameters. | A bit on the prediction |  | Developer | Moderate |  | Closed | Risk
2 | Dependency | There is a huge dependancy on the data which has very high value compared to others and may affect the average | Can affect the results of few graphs |  | Developer | Moderate |  | Closed | Assumption
3 | Assumption | For applying predictive algorithms , the test size taken is very small that is about of the actually test size | May change prediction and accuracy a bit like by 3% |  | Developer | Low |  | Closed | Issue
4 | Risk | Path argument to the .py File | If there is a space in the path given as an argument , program wont work as expected. |  | Developer | High |  | Closed | Dependency
5 | Issue | Proper Comments should be included | It is important to add comments |  | Developer | Low |  | Closed
6 | Risk | Digital Marketing technology word having a space at the end as "Digital Marketing " not noticed | Keeps giving errors |  | Developer | Critical |  | Closed | Open
7 | [8 empty] | Closed
8
9 | [8 empty] | Critical
10 | [8 empty] | High
11 | [8 empty] | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24